## Existing
Access | Miles | Existing Conditions
South Park Broad St (E15) Story City | 0 | Located in a city park. Parking facilities are adequate, access is unmarked. Unimproved river access exists just down stream from a small sheet-pile and rock dam. Food, water, and sanitary facilities are nearby. Camping is available at Whispering Oaks Campground on Timberline Road.
E18 Canoe Access E18 (130th St) | 3.7 | A public access at the E18 bridge. Parking facilities are adequate and the access is marked with a canoe landing symbol on E18. Recent improvements include a rocked switchback trail with Geoweb in areas of high erosion.
Anderson Canoe Access 150th St | 6.9 | A public access at the 150th St bridge. Parking is adequate but could use some repairs. There are public access signs on US 69 and at the park entrance. The existing launch/landing area is muddy and washing away. Broken concrete slabs provide some stabilization, but uneven footing.
Sopers Mill 170th St | 10.5 | A County Park off 170th St with public access signs on US 69 and at the park entrance. Drive to river from main park road needs grading and additional rock. Unmarked primitive public campsite downstream at Bear Creek.
McFarland Park 180th St |  | Unmarked primitive public campsites. Difficult landing.
East Peterson Park 180th St | 12 | A County Park off 180th St with an old canoe launch/landing area at the bridge. There is no parking and access to the river is steep and often muddy. There are Peterson Park signs on US 69 and at the park entrance. Because of plans to replace this bridge, no launch/landing improvements are proposed at this time.
West Peterson Park 180th St | 12.5 | A County Park off 180th St with ample parking, and temporary sanitary facilities during the summer season. There are Peterson Park signs on US 69 and at the park entrance. River access is reasonably good though often muddy.
US Filter Dam Arrasmith Trail |  | An unmarked dam and portage. Existing portage is across concrete dam apron with space for only 1 or 2 boats and no staging area. Strong eddy currents below dam may sometimes take paddlers by surprise. Private property.
Sleepy Hollow Access W Riverside Rd | 15.5 | A public access off West Riverside Road. Parking is adequate and the access is marked with a canoe landing symbol on Riverside. Restrooms will soon be available in nearby Ada Hayden Park. Existing geoweb ramp estimated to be 12 years old & needs repair.
North River Valley Park E 13th St Ames | 18 | Located in a city park with rest rooms and water nearby. Food and other services are available near Interstate 35 and in Ames. Parking is adequate. A "Dam Ahead" sign marks the access from the river and a "Skunk River Water Trail" sign marks the access from a park road. This is the end of the existing water trail.
Youth Sports Complex Billy Sunday Rd Ames | 20.9 | Public land at the end of Billy Sunday Road. On-road parking is adequate since this is not a through street. Sanitary facilities may be available at the Sports Complex. A mowed path provides ready access to the river, but the access is unimproved.
265th Street | 24.3 | There is no public access at this time and no off-street parking. The County plans to replace the bridge in fiscal year 2005 and additional right of way will be acquired at that time. This is the best intermediate access point between the Youth Sports Complex and Askew Bridge.
Skunk River Flats |  | Unmarked public land.
Askew Bridge R70 | 27.8 | Public land acquired when the R70 bridge was replaced. Parking is adequate. Challenging access on steep bank.

## Improvements
Access | Improvements
South Park Broad St (E15) Story City | Taper dam on the downstream side to improve safety. Use existing and new rock. Stabilize bank on access with geoweb and rock. Install access sign and kiosk.
E18 Canoe Access E18 (130th St) | Extend trail at switchback turnaround and trim tree. Install access signs, kiosk and bridge signs.
Anderson Canoe Access 150th St | Stabilize existing access with rip rap, Geoweb, and rock. Remove tree which is about to slump in to the river. Improve parking area. Install access signs, bridge signs, and kiosk.
Sopers Mill 170th St | Provide rock for drive and parking. Install access signs, bridge signs, landing sign and kiosk.
McFarland Park 180th St | Install landing sign and construct Geoweb and rock landing at McFarland Park campsites.
East Peterson Park 180th St | Install bridge signs and indicate landing ahead at West Peterson Park.
West Peterson Park 180th St | Construct new Geoweb and rock launch/landing area. Install access signs, landing sign, and kiosk.
US Filter Dam Arrasmith Trail | Install a portage sign and establish a portage trail for safe passage.
Sleepy Hollow Access W Riverside Rd | Construct a concrete walkway to provide a wheelchair-accessible launch/landing area and fishing access. Install access signs, bridge signs, and kiosk directing users to nearby facilities.
North River Valley Park E 13th St Ames | Construct a concrete walkway along river from the dam and parking area to the existing landing to provide a wheelchair-accessible take-out and fishing access. Install signs and kiosk to direct users to restrooms, water, portage route, and other nearby facilities.
Youth Sports Complex Billy Sunday Rd Ames | Install Geoweb and rock to provide safe river access. Install access sign and kiosk. This access will also provide for a take-out from Squaw Creek which enters the Skunk just upstream.
265th Street | Construct new public access and parking when existing bridge is replaced. Access construction, signs and kiosk are provided for in this proposal.
Skunk River Flats | Provide sign indicating public land to those on the river.
Askew Bridge R70 | Establish Geoweb and rock launch/landing area near mouth of a small creek. Install access signs and kiosk.

## Details
Access | Water Trail Signs | Bridge Signs | Landing Sign | Portage Sign | Sign Installation (hrs) | Kiosk | Excavation (cubic yds) | Paving (sq yds) | Class E Rock (tons) | 2-3 inch Rock (tons) | Class A Rock (tons) | Geoweb (sq yds) | Erosion Control Seeding (acres) | Project Coordinators (hrs) | Engineering (hrs) | Volunteer Labor (hrs) | Machine Time (hrs) | Steve Lekwa (hrs) | Carol Williams (hrs) | Bob Sperry (hrs) | Kevin Shawgo (hrs) | Mark Jackson (hrs) | Volunteer Labor (hrs) | Volunteer Labor kiosks installation (hrs)
South Park Broad St (E15) Story City | 1 | 0 |  |  | 2.5 | 1 |  |  | 50 | 15 |  | 20 |  |  |  | 24 | 4 |  |  |  |  | 3 | 20 | 4
E18 Canoe Access E18 (130th St) | 3 | 2 |  |  | 12.5 | 1 |  |  |  | 15 |  |  |  | 3 |  | 10 |  |  | 3 |  |  |  | 6 | 4
Anderson Canoe Access 150th St | 3 | 2 |  |  | 12.5 | 1 |  |  | 15 | 15 |  | 20 |  | 3 |  | 24 | 8 |  | 3 |  |  |  | 20 | 4
Sopers Mill 170th St | 3 | 2 | 1 |  | 15 | 1 |  |  |  | 30 | 75 |  |  | 3 |  | 4 |  |  | 3 |  |  |  |  | 4
McFarland Park 180th St | 1 |  | 1 |  | 5 | 1 |  |  |  | 15 |  | 30 |  | 3 |  | 34 | 4 |  | 3 |  |  |  | 30 | 4
West Peterson Park 180th St | 4 | 2 | 1 |  | 17.5 | 1 |  |  |  | 15 |  | 30 |  | 3 |  | 34 |  |  | 3 |  |  |  | 30 | 4
US Filter Dam Arrasmith Trail |  |  | 1 | 1 | 5 | [8 empty] | 7 |  | 8 | 4 | 4 | 3 |  |  |  | 8 | 0
Sleepy Hollow Access W Riverside Rd | 5 | 2 |  |  | 17.5 | 1 | 300 | 120 |  |  | 8 |  | 0.5 | 5 | 4 | 14 | 4 | 2 | 3 | 4 |  |  | 10 | 4
North River Valley Park E 13th St Ames | 3 | 2 |  | 1 | 15 | 1 |  | 120 | [6 empty] | 5 | 4 |  |  |  |  | 5 |  |  | 4
Youth Sports Complex Billy Sunday Rd Ames | 2 | 4 | 1 |  | 17.5 | 1 |  |  |  | 15 |  | 30 |  |  | 1 | 34 | 4 |  |  |  | 1 |  | 30 | 4
265th Street | 3 | 2 |  |  | 12.5 | 1 |  |  |  | 15 | 100 | 30 | 0.5 | 4 | 5 | 34 | 8 | 1 | 3 | 5 |  |  | 30 | 4
Skunk River Flats | 1 |  | 1 |  | 5 | [8 empty] | 3 |  | 0 |  |  | 3 |  |  |  |  | 0
Askew Bridge R70 | 3 | 2 | 1 |  | 15 | 1 |  |  |  | 30 |  | 60 |  | 4 |  | 64 | 4 | 1 | 3 |  |  |  | 60 | 4
Total | 32 | 20 | 7 | 2 | 152.5 | 11 | 300 | 240 | 65 | 165 | 183 | 220 | 1 | 38 | 15 | 288 | 40 | 8 | 30 | 9 | 6 | 3 | 244 | 44
Unit Cost | 30 | 20 | 20 | 20 | 20 | 425 | 7 | 30 | 30 | 12 | 12 | 20.16 | 1000 | 40 | 60 | 10 | 50 | 40 | 40 | 60 | 60 | 60 | 10 | 10
Subtotal Item Cost | 960 | 400 | 140 | 40 | 3050 | 4675 | 2100 | 7200 | 1950 | 1980 | 2196 | 4435.2 | 1000 | 1520 | 900 | 2880 | 2000 | 320 | 1200 | 540 | 360 | 180 | 2440 | 440
Project Total | [15 empty] | Project Total | 37426.2
In kind | [15 empty] | In kind | 8300
Total Grant | [15 empty] | Total Grant | 29126.2

## Timeline
| Skunk River Water Trail Grant Proposal | Attachment F
Based on a Project Start Date of October 2004
Access | Improvements | Completion Schedule
South Park Broad St (E15) Story City | Taper dam on the downstream side to improve safety. Use existing and new rock. Stabilize bank on access with geoweb and rock. Install access sign and kiosk. | Summer 2006
E18 Canoe Access E18 (130th St) | Extend trail at switchback turnaround and trim tree. Install access signs, kiosk and bridge signs. | Summer 2005
Anderson Canoe Access 150th St | Stabilize existing access with rip rap, Geoweb, and rock. Remove tree which is about to slump in to the river. Improve parking area. Install access signs, bridge signs, and kiosk. | Spring 2005
Sopers Mill 170th St | Provide rock for drive and parking. Install access signs, bridge signs, landing sign and kiosk. | Summer 2005
McFarland Park 180th St | Install landing sign and construct Geoweb and rock landing at McFarland Park campsites. | Summer 2006
West Peterson Park 180th St | Construct new Geoweb and rock launch/landing area. Install access signs, landing sign, and kiosk. | Fall 2005
US Filter Dam Arrasmith Trail | Install a portage sign and establish a portage trail for safe passage. | Spring 2006
Sleepy Hollow Access W Riverside Rd | Construct a concrete walkway to provide a wheelchair-accessible launch/landing area and fishing access. Install access signs, bridge signs, and kiosk directing users to nearby facilities. | Fall 2006
North River Valley Park E 13th St Ames | Construct a concrete walkway along river from the dam and parking area to the existing landing to provide a wheelchair-accessible take-out and fishing access. Install signs and kiosk to direct users to restrooms, water, portage route, and other nearby facilities. | Fall 2006
Youth Sports Complex Billy Sunday Rd Ames | Install Geoweb and rock to provide safe river access. Install access sign and kiosk. This access will also provide for a take-out from Squaw Creek which enters the Skunk just upstream. | Fall 2006
265th Street | Construct new public access and parking when existing bridge is replaced. Access construction, signs and kiosk are provided for in this proposal. | Fall 2006
Skunk River Flats | Provide sign indicating public land to those on the river. | Spring 2005
Askew Bridge R70 | Establish Geoweb and rock launch/landing area near mouth of a small creek. Install access signs and kiosk. | Fall 2005